## Tasks
No | Tasks and desicion | Start | Stackholder
1 | Collect all nounce and clear it. Create domain class. | 2020-03-04 | All
2 | Address class. We have created a separate class for two reasons. First, Address fields are the same for both library members and authors, so we anticipate reuse by factoring out an Address class. Second, Address has own fields which are street, City, State and zip. | 2020-03-04 | All
3 | Depends on requirenment create implementation class. We add id for all association classes. Which is needed for easy to access and find. | 2020-03-04 | All
4 | Drawing class diagram | 2020-03-04 | Saraa
5 | Working on UI visual. Create register, list and message Stage as a template and implement from them for all other scenes. | 2020-03-04 | Vo
6 | Configuring and testing our TEAM environment on GitHub | 2020-03-04 | Tushig and Vo
7 | Determine all Stage which we create. And draw actual as basic. Login, CRUDS /create, read, update, delete, search/ concepts on Member, Book, Book-copy, Member, Author and CR concepts on Checkout, Overdue. | 2020-03-05 | Vo
8 | Draw Sequence diagram.Checkout and Add Member. For control mentioned those as a Class name. That means all UI actions are not mentioned in sequence diagram. | 2020-03-05 | Saraa and Tamir
9 | UI super classes for components. Will needed for easy change appearance, same design and same locations of controls. | 2020-03-05 | Tushig
10 | Book implementation | 2020-03-05 | Saraa
11 | Member implemenataion | 2020-03-05 | Tushig
12 | Author implementation | 2020-03-05 | Vo
13 | Book-copy implementation | 2020-03-06 | Vo
14 | Checkout implemenataion | 2020-03-06 | Tushig
14 | Checkout print implementation | 2020-03-08 | Tushig
15 | Overdue implementation | 2020-03-08 | Tushig
16 | Login sequence | 2020-03-07 | Tamir
17 | Add member sequence | 2020-03-07 | Tamir
18 | Add book-copy sequnce | 2020-03-07 | Vo
19 | Checkout sequence | 2020-03-07 | Tamir
20 | Add book sequence | 2020-03-07 | Tamir
21 | Checkout print by member id sequence | 2020-03-07 | Tamir
22 | Overdue list by book ISBN | 2020-03-07 | Tamir